## C1 - 24 Nov
Test cycle | Number | Type | Description | Reported By | Environment | Priority | Status | Able to reproduce? | Assignee | Time | Test result after fixing
1 | 1 | Improvement | Compress image | Vijay |  | low | Completed |  | Vijay | 5 mins | Fixed
1 | 2 | Bug | Alignment in search cards | Vijay |  | low | completed |  | Vijay | 15 mins | Fixed
1 | 3 | Bug | Login/signup button dose not work FireFox | Farzaneh | FireFox | Medium | Completed | Compeleted by Vijay (Was assigned to Saad) | Saad |  | Not fixed
1 | 4 | Improvement | static files path | Farzaneh |  | low | Completed |  | Farzaneh | 1h | Fixed
1 | 5 | Critical Bug | Sending status 200 even after entering wrong login credentials | Vijay |  | High | Completed |  | Imam |  | Fixed
1 | 6 | Bug | Search button in not working without locaion and city : https://www.sfsuse.com/fa17g20/undefined | Farzaneh | All | High | Completed |  | Farrukh | 15min | Fixed
1 | 7 | Improvement | Exchange the location and city fields | Farzaneh | All | low | Completed | Changed in Customer dashboard:vijay | Farrukh
1 | 8 | Bug | bg-footer.jpg not found | Farzaneh | All | Medium | completed |  | Vijay | 1 min | Fixed
1 | 9 | Bug | Password is not encrypted | Farzaneh | All | High | Completed |  | Imam |  | Fixed
1 | 10 | Bug | After successful login the button of signin is still there | Farzaneh |  | High | Completed |  | Farzaneh | 5min | Fixed
1 | 11 | Bug | Wrong redirection from signup page to home page - click on Home link | Farzaneh |  | High | Completed | Working well now in local will know after pulling latest code | Farzaneh | 5 min | Fixed
1 | 12 | Bug | Bootsrap-select.js wrong path | Farzaneh |  | High | Completed | Not able to produce in local | Farzaneh | 5 min
1 | 13 | Bug | There is no notofication after sending a listing request | Farzaneh |  | Medium | Completed |  | Vijay | 20 mins | Fixed
1 | 14 | Bug | Customer Image is not displaying | Farzaneh |  | Medium | completed | Did not implement Images feature | Vijay
1 | 15 | Bug | Signout button is missed in Dashboard page | Farzaneh |  | low | Completed | Not a bug Improvement | Vijay |  | Fixed
1 | 16 | Bug | There is list of users in Customer dashbord: Vijay,Praveen,...It should display inbox items | Farzaneh |  | High | Completed | Static data as APi is not there | Imam |  | Fixed
1 | 17 | Bug | Logout dose not work for customer | Farzaneh | Safari | High | Completed |  | Farzaneh | 10min | Fixed
1 | 18 | Bug | Delete listing failed : ReferenceError: callback is not defined at Query._callback (/home/fa17g20/core/listing.js:71:18) at Query.Sequence.end (/home/fa17g20/node_modules/mysql/lib/protocol/sequences/Sequence.js:88:24) at Query._handleFinalResultPacket (/home/fa17g20/node_modules/mysql/lib/protocol/sequences/Query.js:139:8) | Farzaneh |  | High | Completed |  | Imam
1 | 19 | Bug | Listing directly displayed without Agent approval | Farzaneh |  | High | Completed |  | Imam |  | Fixed
1 | 20 | Bug | Editing listing is not working : Update Listing request received. 0¦HouseBid ¦ Error in Database Server: Error: ER_TRUNCATED_WRONG_VALUE: Incorrect datetime value: '' for column 'expiry_date' at row 1 | Farzaneh |  | High | Completed |  | Farzaneh
1 | 21 | Bug | Agent Dashbord tabs change without refreshing the content | Farzaneh |  | High | Completed | Need more Description - Farzaneh : By clicking on tab recall ajax to refresh the contect of tab |  |  |  | added only for manage listing
1 | 22 | Bug | No nitification after list posting by agents | Farzaneh |  | Medium | Completed |  | Vijay |  | Fixed
1 | 23 | Bug | City name should be chosen by a drop down list as home page | Farzaneh |  | High |  | In which tab? | Vijay
1 | 24 | Bug | Login failed message after trying to post a listing : POST request for /fa17g20/agent/listing 0¦HouseBid ¦ Add Profile request received. 0¦HouseBid ¦ Error in Database Server: Error: ER_TRUNCATED_WRONG_VALUE: Incorrect datetime value: '' for column 'expiry_date' at row 1 | Farzaneh |  | High | Completed |  | Farzaneh
1 | 25 | Bug | Expiry date is not stored in DB | Farzaneh |  | Medium | Completed |  | Farzaneh
1 | 26 | Bug | Data failed message for listing update | Farzaneh |  | High | Completed |  | Vijay |  | Not fixed | You have tp give all details as all are mandatory did not put Validations
1 | 27 | Bug | City drop down CSS dose not work in home page and listing page | Farzaneh |  | Medium | Compelted | Need more details : Sometime is rendering like this ---> image |  |  | Not fixed | Removing the Dropdown as its not working most of the time
1 | 28 | Bug | Additional details/ features/photos are the same for all listings | Farzaneh |  | High | Completed | If picture is not uploaded default picture is loaded:vijay | Vijay
1 | 29 | Bug | Listing details starts with Villa !! | Farzaneh |  | Medium | Completed |  | vijay |  | Fixed
1 | 30 | Bug | Sorts are not working: backend and front end not implemented | Farzaneh |  | High | Completed |  | Farzaneh
1 | 31 | Bug | search filter is reset to default after clicking on search button | Farzaneh |  | Medium
1 | 32 | Bug | Agent dashbord should be sortable for bid price :backend and front end not implemented | Farzaneh |  | High |  | Will not be able to do this. | vijay & imam
1 | 33 | Improvement | activate enter key for search | Farzaneh |  | high |  | Should keep a listner fo every key press | vijay

## C2 - 7 Dec
Test cycle | Number | Type | Description | Reported By | Environment | Priority | Status | Able to reproduce? | Assignee | Time | Test result after fixing
2 | 34 | Bug | Agent List is empty for posting listing | Farzaneh |  | high |  | Must be working now | imam
2 | 35 | Bug | Page redirection : vijay you have spoilt my fix for redirection; You have used APIENDPOINT for api which iwas using last week itself you have told to use relative path so i used it. I was using relative path from the start | Farzaneh |  | high | Completed |  | Farzaneh | 5m | Fixed
2 | 36 | Bug | Delete Button in edit listing dose not work | Farzaneh |  | high | Completed |  | Vijay |  | Fixed
2 | 37 | Improvement | Add City to listing cards | Farzaneh |  | high | Completed |  | Vijay |  | Fixed
2 | 38 | Bug | Bid is not sent | Farzaneh |  | Medium | Completed | Need more details: When user enters a number for bid it should be sent as a message to the agent (a message including bid) | Vijay |  | Fixed
2 | 39 | Improvement | Make font files Local | Vijay |  | Medium | Completed | Fixed the Url error | Vijay
2 | 40 | Improvement | Restrict negative values | Vijay |  | High | Completed |  | Vijay
2 | 41 | Improvement | Improve Search & filter UI | Vijay |  | Medium | Completed |  | Vijay

## C3 -13 Dec
Test cycle | Number | Type | Description | Reported By | Environment | Priority | Status | Able to reproduce? | Assignee | Time | Test result after fixing
3 | 42 | Bug | Failed to load resources: https://fonts.googleapis.com/%20%20%2 0css?family=Bowlby+One+SC¦Poppins , bootstrap-select.js.map | Farzaneh |  | Medium |  |  | Vijay
3 | 43 | Bug | User profile is not displaying | Farzaneh |  | Medium |  | Please check again | Vijay |  | Fixed
3 | 44 | Improvement | Add user name to page header | Farzaneh |  | High
3 | 45 | Bug | Signup button dose not have properCSS | Farzaneh | FireFox | Medium | Completed |  | Vijay |  | Fixed
3 | 46 | Bug | Email Id should not be editable front-end and back-end | Farzaneh |  | High | Completed |  | Vijay |  | Fixed
3 | 47 | Bug | User-type should not be passed to /signup : security problem | Farzaneh |  | Medium |  | How do we handle this?
3 | 48 | Bug | Only current user can edit his profile : security problem | Farzaneh |  | Medium |  | Who else should be allowed to edit?
3 | 49 | Improvement | What is the usage of "https://www.sfsuse.com/fa17g20/user/profile" | Farzaneh |  | Low
3 | 50 | Bug | Extracting City names from existing listing dose not make sense | Farzaneh |  | Medium |  | Imam and farrukh
3 | 51 | Bug | Related to number:19 --> initial status for listing should be inactive not expired | Farzaneh |  | High |  | backend
3 | 52 | Improvement | Remove expiry date from front-end and back-end : there is no need when we have expired as a status | Farzaneh |  | High | Compeleted | Shall we remove this field totally?, it was one of the reason for our application to crash | Farzaneh | 10min | Fixed
3 | 53 | Bug | Sort query is wrong | Farzaneh |  | High |  |  | Imam
3 | 54 | Bug | /agent/listing/update , agenId should not be editable, back-end | Farzaneh |  | Medium
3 | 55 | Improvement | ("Add Profile request received.") for Delete listing | Farzaneh |  | Medium | Compeleted |  | Farzaneh
3 | 56 | Bug | Delete listing fails if there is any dependancy to listing : like message | Farzaneh |  | High | Compeleted | backend
3 | 57 | Bug | listing/image returns 502 if listingId is not found | Farzaneh |  | low |  | Backend
3 | 58 | Bug | listing/image return 502 if there is no image for a listing | Farzaneh |  | High |  | backend
3 | 59 | Bug | update listing should accept images : agent/listing/update | Farzaneh |  | High |  | lesss time to implement this feature
3 | 60 | Improvement | expiry date format : better to delete this field | Farzaneh |  | Medium | Compeleted |  | Farzaneh | 10 min | Fixed
3 | 61 | Bug | Manage Listing and Post listing have the same UI . (?) | Farzaneh |  | High | completed | Didnt understand.. , if the agent had no listings edit listings was shown now i am showing no listings Message | Vijay |  | Fixed
3 | 62 | Bug | Search button is not working without parameters | Farzaneh |  | High |  | Shows all the results | Vijay
3 | 63 | Bug | HOME NEW ACCOUNT / SIGN IN - page header for sign in : remove Home word | Farzaneh |  | Medium | Completed |  | Vijay |  | Fixed
| 64 | Improvement | Expiry date format is not clear : See no 60 --> add validation or date format as placeholder |  |  |  | Completed |  | Farzaneh | 10 min | Fixed
3 | 65 | Bug | City drop down only SOMETIMES shows values | Farzaneh |  | High | Completed | Same reason as 69 bug | Vijay |  | Fixed
3 | 66 | Bug | Listing title is always "Super Nice Villa", it shoud display listing title | Farzaneh |  | High | Completed | Fixed it already last night, Please check again | Vijay |  | Fixed
3 | 67 | Bug | Price, area, bedrooms, biddable display static values | Farzaneh |  | High | Completed | Even though there is static value in html it is replaced by js. removed static values now except for status. | Vijay |  | Fixed
3 | 68 | Bug | Features part is static | Farzaneh |  | High | completed | Yes, Had to fill the page | Vijay
3 | 69 | Bug | Search is not working without parameter, whenever city dropdown list is empty , this problem apprears. | Farzaneh |  | High | Completed | It is beacuse of the timing out bug in server i guess latest pull will fix this, will check for this again after pulling | Vijay |  | Fixed
3 | 70 | Bug | No Listings!!! remains at the botton of page after adding a listing by an agent | Farzaneh |  | Medium | Completed |  | Vijay |  | Fixed
3 | 71 | Bug | Set minum beds and baths to 0 | Farzaneh |  | Medium | Completed |  | Vijay |  | Not Fixed | it will allow to type -1 but it will not go down below 0 when using arrows, cant do more without framework.
3 | 72 | Bug | After editing listing , list of listings shows one item many times. whatsapp image | Farzaneh |  | High | Completed | Not able to reproduce in local : try to update a listing , after hitting cancel/update the initial listing list will be doublicated. | Vijay
3 | 73 | Bug | clicking on manage listing should refresh the list | Farzaneh |  | High | Completed | Need time for this feature | Vijay
3 | 74 | Bug | delete button in edit listing is not working | Farzaneh |  | High | completed | Works iin local | Vijay
3 | 75 | Improvement | Ask confirmation before delete a listing | Farzaneh |  | High
3 | 76 | Bug | Post request by customer : Add Profile request received. TypeError: Cannot read property 'images' of null at /home/fa17g20/core/listing.js:131:42 | Farzaneh |  | High | Completed |  | Farzaneh | 15 min
3 | 77 | Bug | Sorts are not calling backend. | Farzaneh |  | High
3 | 78 | Improvement | Add listing id to bid message | Farzaneh |  | High | Completed |  | VJ |  | Fixed

## C4 - 15 Dec
Test cycle | Number | Type | Description | Reported By | Environment | Priority | Status | Able to reproduce? | Assignee | Time | Test result after fixing
4 | 79 | Improvement | Add listing id to bid message | Farzaneh |  | High | Completed |  | Farzaneh | 15min | Fixed
4 | 80 | Improvement | Rearrange location and listing fields in cus dashboard | Professor |  | Medium | Completed |  | Vijay | 1 min | Fixed
4 | 81 | Improvemnt | add validation for post listing : area -> integer , qoute > price | Farzaneh |  | Medium |  |  | Vijay
4 | 82 | Improvement | Add images for edit listing by agents | Farzaneh |  | High |  |  | Vijay
4 | 83 | Bug | Related to bug 30 : Sort calls from Front-end | Farzaneh |  | High |  | Back end is done : bug 30 | Vijay
4 | 84 | Bug | Search result is not displaying : undefined is not an object (evaluating 'template.find("#listingAreaVal")[0].innerHTML = response[i].area+"m2"') | Farzaneh |  | High | Completed |  | Vijay |  | Fixed
4 | 85 | Bug | Console log : InvalidValueError: initMap is not a function | Farzaneh |  | High | Cant fix | Google maps error | Vijay
4 | 86 | Bug | Console log : Can't find variable: i , main.js | Farzaneh |  | High | Completed |  | Vijay |  | Fixed
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4